## Phase Overview
Phase | Milestone | Week Range | Color Key
Phase 1 | Planning & Requirement Analysis | Week 1-3 | Planning
Phase 2 | UI/UX Design | Week 2-4 | Design
Phase 3 | Core Backend Development | Week 3-10 | Backend
Phase 4 | Core Frontend Development | Week 5-9 | Frontend
Phase 5 | AI Feature Integration | Week 6-11 | AI
Phase 6 | Real-Time Features & Notifications | Week 9-12 | Real-Time
Phase 7 | Continuous Module-Level Testing | Week 5-13 | Testing
Phase 8 | Final Integration, Security & Regression Testing | Week 11 - 13 | Testing
Phase 9 | Deployment & Final Presentation | Week 9-14 | Deployment

## Gantt Chart
Team Member | Task | Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Dev Barot | Finalize requirements & Git/board setup | Planning
Dev Barot | Review UI/UX & validate architecture | Design
Dev Barot | Coordinate backend & frontend integration | Backend
Dev Barot | Facilitate mid-project architecture review & risk log | Backend
Dev Barot | Oversee AI integration into architecture | AI
Dev Barot | Coordinate real-time feature rollout | Real-Time
Dev Barot | Lead testing coordination | Testing
Dev Barot | Oversee deployment & final docs | Deployment
Dhrumil Doshi | Auth & roles requirement gathering | Planning
Dhrumil Doshi | Login/signup/profile wireframes | Design
Dhrumil Doshi | Build JWT auth & RBAC APIs | Backend
Dhrumil Doshi | Profile & settings frontend | Frontend
Dhrumil Doshi | Support marketplace & rental auth checks | Backend
Dhrumil Doshi | Ratings & reputation integration | Real-Time
Dhrumil Doshi | Test auth flows & security | Testing
Dhrumil Doshi | Support auth deployment | Deployment
Nishka Shah | Listing categories & workflow requirements | Planning
Nishka Shah | Listing creation/browsing wireframes | Design
Nishka Shah | Listing CRUD APIs & image upload | Backend
Nishka Shah | Listing/browsing/category UI | Frontend
Nishka Shah | Coordinate listing-to-rental workflow continuity | Backend
Nishka Shah | AI listing suggestions integration | AI
Nishka Shah | Test buy/sell/rent/exchange workflows | Testing
Nishka Shah | Finalize listing module | Deployment
Heer Mehta | AI/OCR research & Groq feasibility | Planning
Heer Mehta | FastAPI AI service scaffolding | Backend
Heer Mehta | Build AI listing/pricing/matching/OCR | AI
Heer Mehta | Support AI-assisted listing feature refinement | AI
Heer Mehta | Redis match-event integration | Real-Time
Heer Mehta | Prepare AI evaluation dataset & benchmark report | Testing
Heer Mehta | Test AI accuracy & matching | Testing
Heer Mehta | Finalize AI service deployment | Deployment
Heer Shah | Search/notification requirements | Planning
Heer Shah | Chat/notification wireframes | Design
Heer Shah | Search API design support | Backend
Heer Shah | Search/filter/wishlist UI | Frontend
Heer Shah | Integrate match-event & rental-reminder triggers | Real-Time
Heer Shah | Socket.io chat & notifications | Real-Time
Heer Shah | Test chat reliability & delivery | Testing
Heer Shah | Finalize search/chat/notification | Deployment
Charmi Bhayani | Rental/transaction requirements | Planning
Charmi Bhayani | Rental/QR handover wireframes | Design
Charmi Bhayani | Rental APIs & transaction state | Backend
Charmi Bhayani | QR code generation/verification | Backend
Charmi Bhayani | Rental dashboard & due-date UI | Frontend
Charmi Bhayani | Rental reminder scheduling | Real-Time
Charmi Bhayani | Test rental/transaction workflows | Testing
Charmi Bhayani | Finalize rental module | Deployment
Kajal Varlani | Admin requirements & moderation workflows | Planning
Kajal Varlani | Admin dashboard wireframes | Design
Kajal Varlani | Admin APIs (approval/dispute) | Backend
Kajal Varlani | Admin dashboard UI & analytics | Frontend
Kajal Varlani | Coordinate analytics data pipeline | Backend
Kajal Varlani | Reporting & moderation notifications | Real-Time
Kajal Varlani | Test admin workflows & disputes | Testing
Kajal Varlani | Finalize admin panel | Deployment
Deep Boghara | DB schema & MongoDB Atlas setup | Planning
Deep Boghara | Schema review vs UI/UX | Design
Deep Boghara | Set up CI pipeline & automated build checks | Backend
Deep Boghara | Support integration & version control | Backend
Deep Boghara | Monitor performance & prep deployment pipeline | Deployment
Deep Boghara | Testing & security checks | Testing
Deep Boghara | Support architecture & release-readiness review | Deployment
Deep Boghara | Manage deployment | Deployment